# CONTRACT TIME CONSIDERATIONS FOR RESURFACING PROJECTS

To calculate the contract time the number of work days must be determined.  In estimating production rates and the number of work days required to do a certain phase of work, consideration is given to the following:

Weather conditions for that area of the state

Size of project in terms of quantities

Number of projects in the area

Availability of materials where material delivery time is the controlling operation

Special construction features or sequences

"Time of year" restrictions for work such as school locations

Heavy congested areas or seasonal traffic areas

Temperature/seasonal limitations for paving, markings (paint, thermoplastic, polyurea)

Taking the above factors into consideration, a production rate is selected for each of the controlling operations.  Using the production rate ranges below as a guide, production rates and overlapping operations are selected which reflect the consideration of the factors listed above.

Resurfacing Production Rate Ranges

| Roadway Operation | Rate Per Working Day |
| --- | --- |
| Asphalt Surface Course | 0.6” to 1” – 500 to 800 tons/day 1” – 500 to 1,000 tons/day |
| Asphalt Intermediate Course | 500 to 1,000 tons/day |
| Asphalt Base Course | 300 to 600 tons/day |
| Asphalt Base Course for Widening or Leveling | 100 to 400 tons/day |
| Asphalt Surface Treatment (AST) | 5,000 to 10,000 SY/day |
| Manhole and Water Valve Adjustments | 8 to 10/day |

The total number of working days, thus computed, can be converted into a completion date by applying the following guides:

- Allow 16 work days per calendar month for projects that are primarily of a type that the controlling operation would be delayed by wet weather or soil conditions.

- Allow 3 months for delays caused by winter weather.

General Items to be Considered When Calculating Contract Time Periods:

Time restrictions for Lane Closures

Work Zone Traffic Control General Requirements

Shoulder reconstruction/construction (ASB, Shoulder Borrow, handwork)

Erosion Control (seeding and mulching)

Milling (depth) and Mill + Fill Requirements

Sidewalk and handicap ramps

Traffic signals and loops

Utility Adjustments

Number of Intersections

Specification Limits to be Observed When Calculating Contract Time Periods

Asphalt Pavement Limitations

| Pavement Type | Limitation Min. Air / Surface Temps. | Reference |
| --- | --- | --- |
| B25.0B, C I19.0B, C, D | 35° | Article 610-4, Table 610-5 revised per Asphalt Superpave SP |
| S4.75A, SF9.5A, S9.5B | 40° | Article 610-4, Table 610-5 revised per Asphalt Superpave SP |
| S9.5C, S12.5C | 45° | Article 610-4, Table 610-5 revised per Asphalt Superpave SP |
| S9.5D, S12.5D | 50° | Article 610-4, Table 610-5 revised per Asphalt Superpave SP |
| OGAFC | 50°/50° (FC-1) 60°/60° (FC-1 Mod. & FC-2 Mod.) None to be placed between October 31 and April 1 | Article 610-5, Page 6-42 |
| AST | 50°F/- None to be placed between October 15 and March 16 except where overlaid with plant mix | Article 660-3, Page 6-49 |
| Surface Course Final Layer | None between December 15 and March 16 if greater than 1” or between November 15 and April 1 if less than 1”. | Article 610-4, Page 6-22 |
| Ultrathin | -/50°F None to be placed between October 31 and April 1 | Subarticle 661-4(C), Page 6-59 |

Marking Limitations

| Marking Type | Limitation | Reference |
| --- | --- | --- |
| Thermoplastic Pavement Markings | 50°F East of I-95: Dec. 15 - March 16 ----- East of I-77 to and including I-95: November 30 - April 1 ----- West of and including I-77: November 15 - April 16 | Subarticle 1205-4(B), Page 12-6 |
| Polyurea Pavement Markings | 40° | Subarticle 1205-5(A), Page 12-7 |
| Paint Pavement Markings | 40°-160° | Subarticle 1205-8(B), Page 12-11 |